- Technical Proposal:

- Skilling and enterprise development in Pune, India

- Executive Summary:

Market Trends in Garments Sector: Garment sector is one of the oldest industries in India. India is the largest producer of raw material (cotton) in the world which creates tremendous scope to dominate the trade across the value chain (fibre to fabric to fashion apparels). The sector is highly diversified with a wide range of products including traditional handloom, handicrafts, wool and silk products to large-scale capital-intensive textile industry that involves spinning, weaving, processing, and apparel manufacturing. The textiles industry contributed 7% to the total industrial output (by value), 2% to India’s GDP, 12% to export earnings and accounted for 5% of the global textile trade in 2018-19. In July 2021, exports of cotton yarn/ fabrics, made-ups, handloom products etc from India increased by 51% over June 2019.

Domestic market: The domestic textile market stood at $100 billion in 2019 and at $108.5 billion in 2019-20 of which $75 billion was domestically consumed while the remaining was exported. India has gained access to better technology and lowered the production costs, as a result of allowing 100 percent foreign direct investment in the sector and huge funding for Integrated Textile Parks (US$ 185 million) and Technology Upgradation (US$ 961 million) released in last 5 years to encourage private equity and provide employment. Production-Linked Incentive Scheme with a financial outlay of INR 106.83 billion. under Atmanirbhar Bharat Package is also boosting the fibre and technical textiles industry. Indian textile industry employs 45 million workers including 3.5 million in handloom sector.

Demand for technical textiles and fashion garments: Owing to the COVID-19 pandemic, the demand for technical textiles - a special segment of textiles - and equipment is on the rise. The government is supporting the sector through funding and machinery sponsoring. Market for technical textiles is expected to expand to US$23.3 billion by 2027. This segment requires labour with special skill sets.

Increase in urbanization, growing penetration of organized retail and e-commerce platforms, favourable demographics and rising disposable incomes is pushing up the demand for fashion garments. As a result, there has been an increase in the demand for more skilled labour (in tailoring, design etc). Many global brands including Marks & Spencer, Guess and Next are opting to manufacture in India because of easy availability of skilled, low cost labour.

Problem Statement: The present workforce is not sufficient to meet the demand. More skilled tailors are needed. Also, the female labour participation rate in India has fallen from more than 26% (2005) to 20.3% (2019), much lower than in Bangladesh (30.5%) and Sri Lanka (33.7%). Over 15 million Indians have lost livelihoods during the economic slowdown that has hit women disproportionately.

Given this scenario, this program aims to enhance the skills of young women, as per the growing demand, help develop their collective enterprises, help them participate in the domestic and global markets and ensure sustainable incomes for their families.

- Statement of the Challenge:

India has a young population (under 25 years) of 600 million, around half of the country’s population. However, only 2.3% of the Indian workforce has had a formal training. This low level of skill, particularly among the women, is a major challenge that creates additional challenges such as lack of secure work (and income) in the organized sector and widening gender inequality. The participation of women in the labour force had fallen to a record low of 15.5% during the April-June 2020 quarter, when India imposed strict lockdown to curb the spread of pandemic. Thus, it is very important to help vulnerable communities recover from the economic shocks of pandemic, through skill development and increased work participation of the youth, particularly girls and women.

- Technical Solution & Approach:

Since the scenario in textile sector may differ across locations, the intervention will be designed with due attention to local market conditions, popular culture and fashion as well as local employment potential.

Target Group and Focus of Training: We propose to focus on urban girls and women. Also, we propose to work on the entire value chain of garment industry. Though the target group typically has the basic knowledge of tailoring, it needs refinement and upgrading to be able to cater to the demand for high value and specialized products. Thus, apart from stitching the clothing, there will be training on technical textiles that are currently in demand. The training will also focus on soft skills and entrepreneurship so that women can grow their business and sustain their business after the project.

Post-training Possibilities: There are three ways in which skill training can possibly empower the participating women and girls:

- Women are trained to get jobs, regular or part time in the market or nearby locations.

- Women are trained to become entrepreneurs by using government schemes and bank loans

- Women are trained to form a cooperative society/ producer organization.

# Geographical Focus:

Girls and women will be identified from the urban poor communities of Pune, Maharashtra. The city will have 3 training-cum-enterprise units (tailoring and designing mainly) with standard infrastructure.

Selection of Areas: The units will be set up in 2 municipal corporation areas (Pune and Pimpri–Chinchwad) and one peri-urban location (Wagholi-Koregaon Bhima). The reason for selecting Pune is that this region — including areas of Pimpri-Chinchwad — has a garment market approximately worth Rs.5,000 crore. Besides this, the industrial area in Pimpri-Chinchwad is a good market.

Target Consumers: There are three major target groups of consumers in Pune: (a) school children, (b) college-going youth and fresh executives, who are regular buyers of fashion garments and casual wear, and (c) industrial workers. Stitching of uniforms is an industry with a lot of potential here due to presence of school children and industrial workers. Uniforms for schools and colleges, industries, restaurants, hotels etc are in high demand. There are around 16.6 lakh school students in the district, with an average requirement of 2 sets of uniforms per year. This makes the school uniform sector worth Rs.1 billion per year. Similarly, there are several major automotive and Information Technology companies and Small and Medium Enterprises (SME) in Pune. All of these need industrial uniforms.

- Goals & Objectives:

The project aims to achieve the following objectives by the end of project period (i.e. Year-1):

- Enhance new skills or strengthen existing skills of 300 women and girls in Pune (Urban),

- Develop at least one collective enterprise of about 25 women with specialized services in machine embroidery and 3-D printing of products for the garment industry.

- Secure the employment for at least 30 percent of trained youths post-training, and work opportunities for at least 50 percent at home

- To achieve, for the enterprises established in Year-1, a profit margin covering at least 25 percent of the total operational cost for Year-2, so as to progressively become fully self-sufficient financially by the end of Year-3

- Create opportunities for girls and women to enjoy independent life due to increase in income and to contribute to household income and gain self-confidence

- PROCESS:

The entire project would involve the following steps:

| - Identification of training locations - Preparation of training materials - Registration of candidates - Counselling - Batch formation | - Training - Post-training Assessment - Certification and Placements - Link with job market & entrepreneurial opportunities - Tracking of Performance |
| --- | --- |

#### These steps/ activities are described below:

#### Activity 1: Preparatory Work

Training Centers: The project will set up 3 training centres around Pune to conduct the training courses.

Training Materials: Training modules will be prepared by Master Trainers and will consist of the Trainer Guide, Candidate Handbook, and other course material. The materials will be prepared in local languages (Marathi and Hindi) and customized as per the profile of targeted trainees. We will use existing knowledge and experiances in content development and design of the training modules.

#### Activity 2: Screening, Selection and Registration of Trainees

Outreach and Publicity of Training Courses: We will advertise the training courses in the target regions through multiple channels to recruit interested candidates. Local cooperatives and community institutions will also be used a medium for popularizing the courses. Meritorious candidates will be offered scholarships apart from some financial support extended to the trainees from Economically Weaker Sections (EWS) to compensate for the loss of their income due to joining the training.

Target Trainees: Candidates will be taken on a first-come, first-serve basis but final selection and registration will follow interviews and screening to identify the most promising candidates. Each batch will consist of approx. 30 people.

#### Activity 3: Conduct Training Courses

Training Duration: Each training course will last 45 days, including classroom training and practicum.

Training Approach: The skills taught during the training will include both technical skills and those related to customer servicing and care, such as basic life skills, soft skills, and business skills. The training methods will develop the competencies expected by apparel manufacturers, their clients, and the industry. The focus of the training will be on the “performance” and competence-building of each trainee. The learning process will be continuously monitored both at the individual level and batch level. Also, feedback will be taken from each trainee. The training will include both theory and practical demonstration of working of the equipment. Demonstrations will cover the popular models of manufacturing equipment and use audio-visual aids. Candidates will be exposed to various live workshops and multimedia presentations so as to provide hands-on experience.

#### Activity 4: Placement of Trainees

Trainees will be placed at various enterprises including those engaged at the beginning of the program. The applicant will help trainees by (a) facilitating work linkages, (b) providing information and (c) facilitating financial inclusion by opening bank accounts and encouraging them to participate in bank-linked savings programmes.

#### Activity 5: Developing enterprise

Steps proposed to develop the enterprise:

- General training on tailoring to women, girls and young men

- Special training on stitching, printing, embroidery requirements of specific products

- Developing linkages with other parts of the value chain for raw material sourcing

- Developing marketing strategies for tapping niche markets, including e-commerce platforms

- Specialization in machine embroidery and printing on fabric to cater to the requirements of customers in niche markets

- Developing women-led enterprises on a cooperative model for manufacturing of specialized products for domestic and export markets

- Seeking design inputs from reputed Indian institutions, such as the National Institute of Fashion Design and National Institute of Design. There are various other forums where our learnings and others learnings could be shared and used. Being close to Mumbai, Pune has the advantage of gaining from the experiences of various similar initiatives.

Team & Division of Responsibilities:

The applicant will deploy a project team constituting the following personnel. In addition to the project team, PCI Senior Leadership team comprising of a group of technical experts will steer the project to ensure that the project maintains the required program quality and adheres to the highest standard of program management and implementation with close scrutiny of measurement data at regular intervals.

| S. No. | Position | Responsibilities |
| --- | --- | --- |
| 1 | Director | Overall supervision of the project Communication with OGI team at Global Communities |
| 2 | Program Manager | Planning the implementation Managing daily operations Providing technical support to activities Collaboration with govt. and partners for smooth implementation Writing reports, lessons and success stories for donors and HQ Assessment and presentation of project progress |
| 3 | Marketing Head | Development of business plan Identification of forward and backward linkages, Bringing business for the enterprise |
| 4 | Center Head | Managing daily operations at the training centre |
| 5 | Trainers | Imparting training to trainees |

Evaluation & Learning:

The applicant will document successes and failures using multimedia resources for indicating the change created by the program, success stories will be highlighted. Case studies will be recorded for the trainees and entrepreneurs who have been involved in the program. We will also conduct focus group discussions periodically to gauge the satisfaction and feedback of the urban poor community in the project areas. We will integrate monitoring and evaluation tasks into the responsibilities of all field staff. This will allow us to regularly collect and analyze data and make the necessary course corrections to ensure that the project outcomes are achieved.

Some of the key impact indicators are:

| Level | Indicator |
| --- | --- |
| Individul | - No. of women and girls trained in various trades - No. of new jobs obtained/ entrepreneurs developed - % of newly employed women reporting an increase in confidence (qualitative) |
| Household | - % increase in the total income of households of entrepreneurs |
| Enterprise | - No. of new loans facilitated for businesses to be started by the trainees - Total revenue (in Rs.) earned through sale of products - % share of e-commerce and mobile apps in total revenue of the enterprise - No. of self-sustaining manufacturing units, created through the project |

Conclusion:

Given the tremendous opportunity to utilize the energy and needs of youth in a largely young country such as India, coupled with enormous policy push and commitment of Government of India for the promotion of textle industry in India, this project will help in bringing the unemployed and inadequately skilled urban youths in the mainstream economic development which will – to some extent – contribute to India’s efforts to become the world leader in the textiles industry. This project has a great scope to succeed by bringing creativity and innovations in business model by focusing on niche markets such as technical textiles and school uniforms.

Endnotes:

Ministry of Textiles, Government of India

Atmanirbhar Bharat stands for Self-reliant India Program

These include PPE kits, handgloves, uniforms, face masks, safety jackets etc.

World Bank Group

Ministry of Statistics & Program Implementation, Government of India

Across the state, industrial areas are developed by MIDC (Maharashtra Industrial Development Corporation). These are well-developed regions, which generate a lot of municipal revenue and are home to high-income group.

School Education And Sports Department Mantralaya, Mumbai (maharashtra.gov.in) (2018-19 data)